SPORT DEVELOPMENT PLAN

A plan should, in essence, answer these questions:

- Where are we now?

- Where do we want to be?

- How are we going to get there?

Your will need a small group of people to drive the sports development plan forward. The planning group will help to ensure that your sports development process is logical and that the final plan is specific, challenging, appropriate and realistic (SCAR) and most importantly, achievable. Your planning group could include people from outside your organisation but everyone involved needs to have time, interest, and vision.

More details can be found on the Home Country Sports Council websites and from your local Sports Development Officer.

The skeleton Sports Development Plan that has been used by a few clubs follows:

| Participation and Access Programme |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| What do you want to achieve? | How are you going to do it? | What's your target and by when? | Who will be responsible? | What's it going to cost? | How will you measure success? | Notes on progress |
| Increased awareness (general programme) | Traditional adverts Static displays Trial lessons | Increase Trial Lessons to 970 by 2003/4 | Marketing sub-Committee | Advertising £2750 | Number of Trial Lessons Target 1999 712 temporary members |  |
| Young People Recruitment | Direct approaches to schools or colleges Junior cadet scheme | Links to be established with 2 schools or colleges p.a. 21 junior members by 2003/4, including 13 on sponsored programme Junior trial lessons to be increased by 10 p.a. (base data to be collected during 1999/2000) | General Committee Marketing Sub Committee | Advertising Sponsorship of junior members' subscriptions and flying costs: at least £3150 in 1999/2000, rising to at least £4550 in 2003/4 | Numbers of links with schools and colleges Number of Junior Trial Lessons Number of Junior pilots |  |
| Women's Recruitment | Direct approaches to relevant groups Adoption of WIG standards (where not already in place) Role models | Increase in female percentage of membership from 10% to 15% by 2003/4 (N.B. National average is 8.5%) | General Committee Marketing Sub Committee Women members | Costs to be assessed during 1999/2000 | Club records - number of women pilots and their levels of integration and achievement |  |
| Disabled Participation | Hoist to lift into gliders Disabled adaptation for two-seat gliders | Hoist operational by end 1999 | Technical Committee | Hoist - approx £500 Adaptation - approx £3,000 | Equipment operational |  |
|  | Clubhouse facilities upgrade for wheelchair and other disabled access | Facilities upgrade, if funds released, by end 2000 | Airfield Group | £1,500 | Completion of alterations and building |  |
|  | Appraisal of means of safely integrating various disabilities into club operations | Appraisal complete by mid 1999 | Operations Group and Safety Officer | Cost of appraisal is minimal. There may be cost implications in upgrading equipment. | Disabled members able to integrate safely and as fully as possible in club operations. |  |
|  | Approaches and promotion to relevant groups | Participation in Trial Lessons 40 by 2003/4 Recruitment of 8 members by 2003/4 | Marketing and membership committees | Minimal additional cost | Numbers participating Club records - number of members |  |
| Ethnic Minorities and disadvantaged groups | Direct approaches and promotion to relevant groups | Increase in participation (Trial Lessons) to 50 by 2003/4 Recruitment of 7 members by 2003/4 | Marketing and membership committees | Minimal additional cost | Number of trial lessons Number of members |  |
| Increase in membership | Retain existing members through mentoring and coaching programme. Recruitment through more focused marketing to generate membership | Increase membership by 5% p.a. to 133 in 1999 137 in 2000 144 in 2001 151 in 2002 157 in 2003/4 | Marketing and membership committees Trial Lesson groups | Advertising costs (see above) | Club membership records |  |
| More sophisticated record keeping | Membership forms to provide additional marketing and social and ethnic information | New forms drafted for 1999 summer season |  | Print costs - estimate £100 | Forms in use |  |
|  | Regular collection of data from forms | Data available from autumn 1999 onwards | Membership secretary |  | Data available |  |
| Social and fund raising activities | Annual Open Days | 70 experience flights | Club committee | 250 per event (advertising costs) | Club records. |  |

Pilot Performance Programme

| What do you want to achieve? | How are you going to do it? | What's your target and by when? | Who will be responsible? | What's it going to cost? | How will you measure success? | Notes on progress |
| --- | --- | --- | --- | --- | --- | --- |
| Performance |  |  |  |  |  |  |
| Improved rate of progress at all levels | Introduction of individual goal setting and mentor/coaching programmes to improve supervision of progress | Targets to be developed in the light of statistics collated in the early part of the programme | Chief Flying Instructor Instructor team and other tutors | Members pay own costs | Availability of relevant statistics. Average rates of progress improving. Reduced level of member drop-out |  |
| Increased number of FAI and BGA badges especially at higher levels | Coaching programmes Training programmes and events for specific achievement levels | Gold badge performance equal to national average by 2003/4; lower levels to continue to match or exceed national averages | Chief Flying Instructor Instructor team and other tutors | Members pay own costs; subsidies for junior members may be required beyond present stage (first solo) | Club and national records |  |
| Increased competition participation | Encourage pilots to visit local competitions to raise interest and knowledge |  | Existing competition pilots, crews and officials to encourage others (particularly juniors) to develop competition experience | Members pay own costs | Pilots' competition activity. Competition results. |  |
| Competition experience | Coaching programmes to incorporate regional competition participation | 1999 - I pilot entering rated comp, increasing by 1 pilot p.a. to 5 pilots in 2003/4 |  | Members pay own costs | Pilots' competition activity. Competition results. |  |
| Competition direction and administration | Encourage members to develop knowledge of officiating at competitions | Members to direct Junior National Champs 1999 and other events in subsequent years | Competition pilots, crews and Stratford GC Official Observers | Members pay own costs | Logging of attendees |  |
| Increased number of pilots flying cross country | Cross country coaching and briefing | 1998 - 16 pilots flew cross country at least once. Increase by 2 pilots p.a. to 26 in 2003/4 | Cross Country soaring and coaching group | Members pay own costs; minimal costs in developing coaching programmes and activities | Club records of cross country flying Achievement of target |  |
| Increased number of pilots taking part in advanced techniques | Individual and group coaching programmes to identify suitable courses and expeditions to develop new techniques and experience | At least 20% taking part each year in: Wave flying Aerobatics Hill and mountain flying | Cross Country soaring and coaching group | Members pay own costs | Numbers taking part FAI and BGA badges and other relevant achievements |  |
| Increased total cross country distances by club pilots | Cross country coaching and regular briefing | 1998 - 7,500 km flown. Increase by 10% p.a. to 12,000 km in 2003/4 | Cross Country soaring and coaching group | Members pay own costs; minimal costs in developing materials for coaching and briefing programmes | Club records of cross country flying Achievement of target |  |
| Expeditions to other gliding sites | Member-organised arrangements | At least one summer and one winter expedition p.a. | Cross Country soaring and coaching group | Members pay own costs | Number of visits and number of pilots involved |  |
| Inter-club league achievements | Team leader to be appointed to organise entries Cross-country soaring and coaching group to coach pilots | 2000 - full team to be entered in every league event 2001 - end of season score < 25% behind winners 2002 - score < 15% behind winners 2003/4 - 1st or 2nd place | Cross Country soaring and coaching group | Members pay own costs; subsidies for junior members may be required + minimal costs for developing materials for coaching programmes | League results. |  |
| Retention of experienced pilots | Provision of high quality launching Keen competitive environment | Lose maximum 1 pilot p.a. to other clubs in period 1999 - 2003/4 | Main Committee. Coaching and soaring group | High performance launching winch essential (£55,000 capital purchase). | Club membership records. Achievement of target. |  |
| More sophisticated record keeping | Establish system to record performance achievements at all levels | Simple paper based or computer system in place for 1999 season | CFI | Costs not yet known | System operational by spring 1999. Data available in autumn 1999. |  |

| Coaching Programme |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Extending instructor qualifications | Introduction of BGA instructor renewal programme. Develop facilities for better ground instruction. Instructor attendance on advanced soaring courses. Qualify additional instructors to full rating | All instructors to attend refresher courses at appropriate intervals. Regular ground instruction to be available. | CFI | Max £500 p.a. for materials and course subsidies. Members to pay other costs themselves. | Number of fully qualified and currently refreshed instructors; quality of training and coaching available to all members. |
| Recruiting additional instructors and soaring tutors | Identify potential candidates and coach them with appropriate training, flying and other experience | 1 newly qualified assistant rated instructor p.a. Qualified instructors and other experienced pilots to be offering regular soaring coaching (on the ground and in the air) | CFI | Subsidy to instructor courses - £500 per candidate | Number of newly qualified instructors; quality of training and coaching available to all members. |
| Introduction (if relevant) of NCF modules | 2 senior instructors to attend appropriate NCF courses to assess value for gliding | Evaluation to be completed by 2000. Strategy for use of modules (if any) to be developed during 2001 | CFI | NCF Course fees | Strategy in place. Relevant NCF courses in use by all instructors. |
| Development of individual and group goal setting and coaching programmes | Coaching selected instructors in techniques. Introduction of performance coaching programme for interested pilots. | Initial introduction of concepts during 1999. Regular coaching programme to develop during 1999 - 2003/4. | CFI | Max £500 p.a. for materials and course subsidies. Members to pay other costs themselves. | Number of members attending coaching programmes. Pilots' subsequent achievements |

| Officials and Administrators |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Training competition officials | Officials' participation at competitions and leagues | Run one Inter-Club League meeting each season | Cross Country soaring and coaching group | Minimal cost for materials for ground instruction and lectures | Well-run events |
| Increase numbers of Official Observers | Recruitment of suitably experienced pilots | O.O.s to represent 10% of membership. | CFI and Cross Country soaring and coaching group | No cost | Numbers of O.O.s reaching target |
| Training Official Observers | Seminars | One seminar p.a. | CFI and Cross Country soaring and coaching group | Minimal cost for materials for ground instruction and lectures | Successful well attended seminars |
| Training of administrators | Investigate availability and value of Running Sport programme | Running Sport programme to be investigated during 1999 | Club Secretary | Not known | Strategy in place. |
| Excellence |  |  |  |  |  |
| Talent identification | Monitor progress of novice pilots (especially young people) | 1 top performer in any 5 - 10 years is realistic | CFI and all instructors | No cost | Talented pilots receiving suitable coaching and making good progress |
| Fast track coaching and development for talented pilots | Individual coaching programmes. Encouraging pilots with potential and talent to work with coaches and other top pilots and to take part in other performance developing activity | Targets can only be defined as relevant pilots are identified. | CFI and all instructors; Cross Country soaring and coaching group | Generally, members pay own costs. Possible additional subsidy to junior pilots | Talented pilots receiving suitable coaching and making good progress |
| Encourage talented pilots to enter performance gliding | Individual coaching programmes. Encouraging pilots with potential and talent to enter Junior Nationals and Regional competitions | Targets can only be defined as relevant pilots are identified. | CFI and all instructors; Cross Country soaring and coaching group | Generally, members pay own costs. Possible additional subsidy to junior pilots | Talented pilots entering competitions and achieving results commensurate with their experience and ability. |
| Encourage talented pilots to move to or visit centres of excellence | Individual coaching programmes | Targets can only be defined as relevant pilots are identified. | CFI and all instructors; Cross Country soaring and coaching group | Members pay own costs. | Talented pilots obtaining wide experience and developing their abilities. |